## blank
777 Working Days | Oct-Dec 24 | Jan-Mar 25 | Apr-Jun 25 | Jul-Sept 25 | Oct-Dec 27 | Jan-Mar 28
Work Package 1
Task 1
Task 2
Work Package 2
Task 1
Task 2
Etc
Work Package 3
Task 1
WPx Transferable Skills
Project Mgt workshop
Career Planning workshop
Presentation Skills wkshop
Ethics & Integrity course
Conference attendance
Task 6
Etc
WPx Write Thesis
Holiday

## lit rev tasks
777 Working Days | Oct-Dec 24 | Jan-Mar 25 | Apr-Jun 25 | Jul-Sept 25 | Oct-Dec 27 | Jan-Mar 28
Work Package 1
Task 1
Task 2
WP2 Lit Review
Read up on background
Define scope
Attend Info Skills
Attend Patent Lit Skills
Attend Ref Mgt Skills
Catalogue articles
Write first draft
Draft to s'visor, then revise
Submit to Materials: PGR Progression
Work Package 3
Task 1
WPx Transferable Skills
Project Mgt workshop
Career Planning workshop
Presentation Skills wkshop
Ethics & Integrity course
Conference attendance
Task 6
Etc
WPx Write Thesis
Holiday

## +timeline
777 Working Days | Oct-Dec 24 |  | Jan-Mar 25 | Apr-Jun 25 | July-Sept 25 | Oct-Dec 25 | Oct-Dec 27 | Jan-Mar 28 | Apr-Sept 28
Work Package 1
Task 1
Task 2
WP2 Lit Review
Read up on background
Define scope
Attend Info Skills
Attend Patent Lit Skills
Attend Ref Mgt Skills |  | a1
Catalogue articles |  | a2
Write first draft |  |  | ? | ?
Draft to s'visor, then revise
Submit to Materials: PGR Progression
Work Package 3
Task 1
WPx Transferable Skills
Project Mgt workshop
Career Planning workshop
Junior Demonstrating wkshop
Presentation Skills wkshop
Ethics & Integrity course
Conference attendance
Task 5
Etc
WPy Milestones & Related
Colloquia
Assessed Lecture Courses
Grad Student Questionnaire | Week 4 MT
Meet Dept Advisor | Week 7 MT
Submit GSR report | Week 7-9 MT
Upload PMF 1 |  |  | Week 0-1 HT
Submit GSR report |  |  | Week 7-9 HT
Meet Lead Assessor |  |  |  | Week 2-4 TT
Submit GSR report |  |  |  | Week 7-9 TT
Upload Literature Review |  |  |  | Week 8 TT
Upload PMF 2 |  |  |  |  | July
Submit GSO.2 application |  |  |  |  | July
Submit GSR report |  |  |  |  | mid-Sept
Transfer of Status interview |  |  |  |  | mid-Sept to Wk 1 MT | Latest date Week 1 MT
Submit GSR report | [5 empty] | Week 7-9 MT
Upload PMF 3a
Submit GSR report
Research Talk
Submit GSR report
Upload PMF 3b
Submit GSR report
Submit GSO.14 application
Submit GSR report
Upload PMF 3c
Submit Poster
Submit GSR report
Confirmation of Status interview
Submit GSR report
Upload PMF 3d
Submit GSR report
Upload PMF 4 | [6 empty] | Week 0-1 MT
Submit GSR report | [6 empty] | Week 7-9 MT
Submit GSO.3 application
Submit GSR report | [7 empty] | Week 7-9 HT
Submit thesis
DPhil viva
WPz Write Thesis
Outline Contents
Six weeks before thesis submission submit on-line GSO.3 form (Application for Appointment of Examiners)
Task 3
Task 4
Etc
Submit thesis
Holiday
a = linked
To capture your actual research you will have a number of Work Packages, often each containing several tasks (and even sub-tasks if you wish)